Youth Homelessness Prevention Plan Committee

Monday, October 22nd, 2018

1pm-3pm

Hartford Town Hall, 171 Bridge Street, WRJ

Present: Lauren (TAC), Ari (VCRHYP), Keegan (YAB), Judy (DCF, Co-chair), Nic (NCSS), Tracy (VDOL), Will (SYFS), Katie (Junction), Jakya (YAB), George (OEO), Daniel (VSHA), Tara (WCYS), Ellen (UVH), Jesse (AOE), Melissa (YS), Wendi (YS), Lacey (YAB), Devon (YAB), JR (YAB), Kara (Network), Bethany (VCRHYP, Co-chair), Sara (HPC)

Updates to Meeting Schedule

We are extending some of our future meetings so that we can complete the CCP that is due, in final form, in March. In November, we’ll finalize our statement of need after diving into the data we’ve been collecting. We’ll finalize goals and objectives in December and do some project brainstorming. In January, we’ll finalize the projects that we’ll include in the plan and then complete the Continuous Quality Improvement plan. We’ll submit the plan to the CoC Board in February for a vote before submitting to HUD. HUD has committed to turning around CCP comments within 6-10 days after our first draft is submitted, which will be helpful.

Everyone should hold 10-3 for the November meeting, but as the planning progresses, we’ll reach out if that changes. We may hold a YAB meeting that day, so committee members may not need to be present until later in that day. Keep your eyes open for more information.

Decision-making Structure

At our last meeting we finalized the broader governance structure that shows how YHPPC, the Leadership Team, YAB, and VCEH interact with one another. Today’s plan is finalize the governance structure of the YHPPC. The Leadership Team is presenting two options:

- Option 1: Weighted stakeholder group structure. The stakeholder groups represent those who are around the table now and need to remain at the table. Most of the groups have a weight of one, but some of the groups have a weight of two, such as the RHY providers. The expectation would be that if there were more than one organization in a stakeholder group, they would discuss the vote ahead of time and come to an agreement.

- Option 2: One organization = one vote. This is a more traditional model where each organization currently on the committee has one vote. There are some questions that need to be answered if we move forward with this option, such as what happens if new organizations join the committee down the road.

Discussion

- Is there a reason why Spectrum is included in Option 1 as Chittenden representative instead of RHY provider?

  - This is to recognize that Spectrum has been representing the needs/perspectives of Chittenden County, but that the demo project funding cannot be used in that county.

- Is there a plan for recruiting a LGBTQ and pregnant/parenting representative?

  - Yes, outreach to Outright VT and the Department of Health has been done. Outright VT is able to participate. The Department of Health has pointed us in the direction of Lund, so we’ll outreach to them.

- Option 1 provides more detail and seems more informative.

- Option 2 runs into the possibility of certain stakeholders being overrepresented since some groups may be able to send more people to the table than others.

- Option 1 helps us recruit representatives if certain organizations are no longer participating.

Final decision by the group: Option 1 – Weighted Stakeholder Groups

YHDP Action Items

The CCP requires having a shared vision. Today we’ll talk about what a vision is and what it means. This vision will guide our work together. The CCP also requires one goal, one objective, one action step, and who is responsible for that action step.

Vision Statement

The vision statement should define the aspirational goal for the group. Think big picture about what Vermont’s BoS looks like when youth homelessness is ended. This vision can guide system transformation and assist you in making hard decisions. It also provides clarity when bringing this plan to other stakeholders. This about: What does the end of youth homelessness look like? What are we aspiring to at the highest level? What conditions will put your organization out of a job?

The vision included in our YHDP application was: “The plan’s overarching objective is to target systems, services, and supply to make youth homelessness rare, brief, and non-recurring.” You’ll notice in reviewing round 1 communities that there is sometimes the inclusion of “equity.” Some communities felt it was important to recognize equity for different subpopulations. Many of the round 1 communities have vision statements that are as simple as ours.

Discussion

- Interesting to note that this vision mentions making youth homelessness rare, but not ending it.

- Saying that someone is housed doesn’t recognize the quality of their housing. Statistics that measure how many people move into housing don’t tell us whether their housing is safe and of high quality. Adding in language about youth thriving could capture this.

- Suggest adding "safe” in front of systems and “nondiscriminatory” in front of services.

- Need to keep in mind that not everyone who reads this is going to understand it right away. The example from Anchorage goes into more detail and provides more clarity.

Small group discussions to address the three prompting questions and report back to full committee about what is important to include in vision statement:

- Equitable access to support and intervention

- More affordable housing

- Community awareness of resources

- Aspiring to access, accountability of community partners, honoring rural culture, justice, and equity

- Youth voice, choice, and leadership at the forefront

- Accessible

- Uniquely tailored

- Thriving

- Safety

- Belonging

- Consistent, stable, predictable

- Coordinated services

- Prevention

- Being aware that people have different potentials

- Empowerment

- Sense of agency

- Reliability of systems

- Permanent connections

- Equal access

- Coordinated community response

- Sustainable

While not a requirement, other communities have created guiding principles. This may be a place to incorporate elements that don’t make it into the vision statement. These can help project developers know what needs to be included in their project design.

Next steps: Lauren & leadership team will create a few examples of vision statement and guiding principles and put them out to the committee for a vote.

Plan Goals & Objectives

These should be goals for our system. How will you know you’ve achieved your vision? HUD only requires one goal, but all Round 1 communities put in more than one.

One option is to use USICH’s 5 criteria and benchmarks to end youth homelessness and then define how we’re going to operationalize them. This would help the community if you decide to seek recognition from USICH about having successfully ended youth homeless. Additionally, a variety of departments helped draft these benchmarks, which can be helpful when talking with our stakeholders. A second option is to use USICH’s 4 core outcomes, which is what we originally used in our framework. Some communities also incorporated elements from both the criteria/benchmarks and outcomes. Another option would be to start from scratch and create our own.

Discussion

- Should we be using the data we have collected to draft our goals and objectives?

- It is okay for the goals to be broader and then incorporate what the data is telling us into the action steps.

- Interested in building in elements from Santa Cruz’s example, such as the emphasis on prevention and diversion.

- Want to see social & emotional well-being included.

- Want to make sure to incorporate system outcomes as well.

Final decision by the group: Use USICH’s 4 outcomes, but build onto them to incorporate some additional elements

Group discussion of elements to include in each outcome area:

- Stable housing: change to “Housing Continuum”

- Full potential

- Outreach to permanent housing

- Accessible

- Effective, appropriate options

- Safety/thriving

- Sustainable

- Non-discriminatory

- Permanent Connections

- Family of choice

- Opportunities to be integrated into community

- Natural and intentional mentors

- Caring adult to support trajectory

- Respect towards youth

- Outreach and communication (objective)

- Education/Employment

- Removal of barriers

- Support to pursue all options

- Access to after school support

- Third space activities (not in family or school)

- Support to understand their rights

- Holistic support for students/new employees

- Increase paid learning opportunities (objective)

- Social/Emotional Well-being

- Support youth to develop skills

- Intentional recruitment and encouragement

- Normalization of negativity, bringing in trauma-informed lens

- Training for all housing providers around human development’s impact

- Self-advocacy

- More to learn

- More mental health counselors (objective)

- Meeting youth where they’re at

- Building resiliency and protective factors

- Education about community resources

- Prevention/Diversion

- Families of choice

- Investment in prevention is important: prevents the crisis from happening

- Community outreach to identify youth at risk

- Wide ability to access

- Ability to identify and monitor risk factors

- Look at intergenerational risk for future homelessness

- Speediness

- Empowerment

Next step: Lauren and leadership team will draft the objectives and send out to full committee for review.

True Colors Fund Youth Collaboration Visit: December 10th  – 11th

Khalib and Ziggy will be here to host a youth collaboration visit. The first day will focus on authentic youth collaboration for adult providers. The second day will be for members of the Youth Action Board, with a listening-only session for adult supporters in the afternoon. More information will be shared as we have it.

Hiring Update

We were hiring for the YHDP Coordinator position, but ended that process when VCRHYP lost one of its funding sources. VCRHYP will now have the capacity to take this role on internally. Bethany and Ari are currently determining their specific roles, but Bethany will be the primary YHDP contact.

Upcoming meetings

11/26 		YHPPC meeting, 10-3 Hartford Town Hall

12/10-11 	Youth Collaboration Intensive w/ True Colors Fund, Location TBD

    - Day 1 for adult partners

    - Day 2 for YAB members, with listening-only session for adult partners in afternoon

12/17 		YHPPC meeting, 10-3, Hartford Town Hall

1/28 		YHPPC meeting, 10-3, Hartford Town Hall

2/25 		YHPPC meeting, 1-3, Location TBD